## RAM
WBS Element/Personnel | Work Package Type | Work Package | Project Manager | Hardware | Software | Testing | Sponsor | Other | Work Package Duration (Days) | Work Package Labor (Person Hours)
project | Project
Market Analysis | Phase
Materials Research | Activity
Battery Research | Activity
Battery Types | Activity
Lithium Ion | Activity
Cell Chemistry | Subtask | 1.1.1.1.1.1.1
Cathode Materials | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Anode Materials | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Electrolyte Composition | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Form Factor | Subtask | 1.1.1.1.1.1.1
Cylindrical | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P |  |  | 2 | 16
Prismatic | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P |  |  | 2 | 16
Pouch | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P |  |  | 2 | 16
LiFePO4 | Activity
Safety Features | Subtask | 1.1.1.1.1.1.1
Thermal Management | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Overcharge Protection | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Short Circuit Prevention | Subtask | 1.1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Battery Capacity | Subtask | 1.1.1.1.1
Power Requirements | Subtask | 1.1.1.1.1.1 | R | L | P | P | I |  | 2 | 16
Usage Duration | Subtask | 1.1.1.1.1.1 | R | L | P | P | I |  | 2 | 16
Size Constraints | Subtask | 1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Battery Safety | Subtask | 1.1.1.1.1
Temperature Control | Subtask | 1.1.1.1.1.1 | R | L | P | P | I |  | 2 | 16
Protection Circuits | Subtask | 1.1.1.1.1.1 | R | L | P | P | I |  | 2 | 16
Certification Requirements | Subtask | 1.1.1.1.1.1 | L | P |  | P | I |  | 2 | 16
Battery Suppliers | Subtask | 1.1.1.1.1
Vendor Selection | Subtask | 1.1.1.1.1.1 | L | P |  |  | I |  | 2 | 16
User Needs Analysis | Phase
Target Audience Research | Subtask | 1.1.1
Demographics | Subtask | 1.1.1.1 | L |  |  |  | I | P | 2 | 16
Usage Patterns | Subtask | 1.1.1.1 | L |  |  |  | I | P | 2 | 16
Purchase Behavior | Subtask | 1.1.1.1 | L |  |  |  | I | P | 2 | 16
User Pain Points | Subtask | 1.1.1
Current Solutions | Subtask | 1.1.1.1 | L | P | P |  | I |  | 2 | 16
Unmet Needs | Subtask | 1.1.1.1 | L | P | P |  | I |  | 2 | 16
Feature Requests | Subtask | 1.1.1.1 | L | P | P |  | I |  | 2 | 16
Build | Phase
Component Sourcing | Activity
Battery Procurement | Subtask | 1.1.1.1
Supplier Selection | Subtask | 1.1.1.1.1 | L | P |  |  | I |  | 2 | 16
Project Totals |  |  | Key
Total WBS Boxes: | 42 |  | L = Lead | P = Participant | R = Reviewer | I = Input | Project | Phase | Activity | Subtask*
Total Phases: | 3 |  | * Subtask rows are colored to match their corresponding level in the WBS diagram
Total Activities: | 6
Total Work Packages: | 32