## RAM
WBS Element/Personnel | Work Package Type | Work Package | Project Manager | Hardware | Software | Testing | Sponsor | Other | Work Package Duration (Days) | Work Package Labor (Person Hours)
SelfiePod | Project
Market Analysis | Phase
Materials Research | Activity
Battery Research | Task
Battery Types | Task
Lithium Ion | Task
Cell Chemistry | Task
Cathode Materials | Subtask | 1.1.1.1.1.1.1 | R | L |  | P | I |  | 2 | 16
Anode Materials | Subtask | 1.1.1.1.1.1.2 | R | L |  | P | I |  | 2 | 16
Electrolyte Composition | Subtask | 1.1.1.1.1.1.3 | R | L |  | P | I |  | 2 | 16
Form Factor | Task
Cylindrical | Subtask | 1.1.1.1.1.2.1 | R | L |  | P |  |  | 2 | 16
Prismatic | Subtask | 1.1.1.1.1.2.2 | R | L |  | P |  |  | 2 | 16
Pouch | Subtask | 1.1.1.1.1.2.3 | R | L |  | P |  |  | 2 | 16
Safety Features | Task
Thermal Management | Subtask | 1.1.1.1.2.1.1 | R | L |  | P | I |  | 2 | 16
Overcharge Protection | Subtask | 1.1.1.1.2.1.2 | R | L |  | P | I |  | 2 | 16
Short Circuit Prevention | Subtask | 1.1.1.1.2.1.3 | R | L |  | P | I |  | 2 | 16
Battery Capacity | Task
Power Requirements | Subtask | 1.1.1.2.1 | R | L | P | P | I |  | 2 | 16
Usage Duration | Subtask | 1.1.1.2.2 | R | L | P | P | I |  | 2 | 16
Size Constraints | Subtask | 1.1.1.2.3 | R | L |  | P | I |  | 2 | 16
Battery Safety | Task
Temperature Control | Subtask | 1.1.1.3.1 | R | L | P | P | I |  | 2 | 16
Protection Circuits | Subtask | 1.1.1.3.2 | R | L | P | P | I |  | 2 | 16
Certification Requirements | Subtask | 1.1.1.3.3 | L | P |  | P | I |  | 2 | 16
Vendor Selection | Subtask | 1.1.1.4.1 | L | P |  |  | I |  | 2 | 16
Plastic Types | Task
ABS Analysis | Task
Impact Resistance | Subtask | 1.1.2.1.1.1 | R | L |  | P |  |  | 3 | 24
Heat Resistance | Subtask | 1.1.2.1.1.2 | R | L |  | P |  |  | 3 | 24
Cost Analysis | Subtask | 1.1.2.1.1.3 | L | P |  |  | I |  | 2 | 16
Polycarbonate Study | Task
Durability Tests | Subtask | 1.1.2.1.2.1 | R | L |  | P |  |  | 3 | 24
UV Resistance | Subtask | 1.1.2.1.2.2 | R | L |  | P |  |  | 3 | 24
Manufacturing Process | Subtask | 1.1.2.1.2.3 | R | L |  | P | I |  | 4 | 32
User Needs Analysis | Activity
Target Audience Research | Task
Demographics | Subtask | 1.2.1.1 | L |  |  |  | I | P | 2 | 16
Usage Patterns | Subtask | 1.2.1.2 | L |  |  |  | I | P | 2 | 16
Purchase Behavior | Subtask | 1.2.1.3 | L |  |  |  | I | P | 2 | 16
User Pain Points | Task
Current Solutions | Subtask | 1.2.2.1 | L | P | P |  | I |  | 2 | 16
Unmet Needs | Subtask | 1.2.2.2 | L | P | P |  | I |  | 2 | 16
Feature Requests | Subtask | 1.2.2.3 | L | P | P |  | I |  | 2 | 16
Build | Phase
Component Sourcing | Activity
Battery Procurement | Task
Supplier Selection | Subtask | 2.1.1.1 | L | P |  |  | I |  | 3 | 24
Quality Verification | Subtask | 2.1.1.2 | R | L |  | P |  |  | 4 | 32
Cost Negotiation | Subtask | 2.1.1.3 | L | P |  |  | I |  | 3 | 24
Electronics Components | Task
Component List | Subtask | 2.1.2.1 | R | L | P |  |  |  | 2 | 16
Supplier Quotes | Subtask | 2.1.2.2 | L | P |  |  | I |  | 3 | 24
Lead Time Analysis | Subtask | 2.1.2.3 | L | P |  |  | I |  | 2 | 16
Prototype Development | Activity
Initial Prototype | Task
3D Printing | Subtask | 2.2.1.1 | R | L |  | P |  |  | 5 | 40
Assembly | Subtask | 2.2.1.2 | R | L | P | P |  |  | 4 | 32
Testing | Subtask | 2.2.1.3 | R | P | P | L |  |  | 5 | 40
Final Prototype | Task
Production Methods | Subtask | 2.2.2.1 | L | P |  | P | I |  | 4 | 32
Quality Control | Subtask | 2.2.2.2 | R | P |  | L |  |  | 3 | 24
Documentation | Subtask | 2.2.2.3 | L | P | P | P | R |  | 3 | 24
Electrical Testing | Phase
Power System | Activity
Battery Performance | Task
Charge Cycles | Subtask | 3.1.1.1.1.1.1 | R | P |  | L |  |  | 5 | 40
Voltage Stability | Subtask | 3.1.1.1.1.1.2 | R | P |  | L |  |  | 3 | 24
Temperature Profile | Subtask | 3.1.1.1.1.1.3 | R | P |  | L |  |  | 4 | 32
Circuit Validation | Task
Signal Integrity | Subtask | 3.1.1.1.1.2.1 | R | P | P | L |  |  | 3 | 24
EMI Testing | Subtask | 3.1.1.1.1.2.2 | R | P |  | L |  |  | 4 | 32
Power Efficiency | Subtask | 3.1.1.1.1.2.3 | R | P |  | L |  |  | 3 | 24
MCU Validation | Activity
Clock Stability | Subtask | 3.1.1.1.2.1.1 | R | P | P | L |  |  | 2 | 16
Memory Tests | Subtask | 3.1.1.1.2.1.2 | R | P | P | L |  |  | 2 | 16
Peripheral Tests | Subtask | 3.1.1.1.2.1.3 | R | P | P | L |  |  | 3 | 24
Platform Strategy | Phase
Instagram Campaign | Activity
Content Creation | Task
Photo Shoots | Subtask | 4.1.1.1.1.1.1 | R |  |  |  | I | L | 3 | 24
Video Production | Subtask | 4.1.1.1.1.1.2 | R |  |  |  | I | L | 4 | 32
Story Templates | Subtask | 4.1.1.1.1.1.3 | R |  |  |  | I | L | 2 | 16
Influencer Program | Task
Selection Criteria | Subtask | 4.1.1.1.1.2.1 | L |  |  |  | I | P | 2 | 16
Engagement Metrics | Subtask | 4.1.1.1.1.2.2 | L |  | P |  | I | P | 2 | 16
ROI Analysis | Subtask | 4.1.1.1.1.2.3 | L |  | P |  | I | P | 3 | 24
TikTok Strategy | Activity
Trend Analysis | Subtask | 4.1.1.1.2.1 | R |  |  |  | I | L | 2 | 16
Content Calendar | Subtask | 4.1.1.1.2.2 | R |  |  |  | I | L | 2 | 16
Performance Metrics | Subtask | 4.1.1.1.2.3 | R |  | P |  | I | L | 2 | 16
Automation Systems | Phase
Robot Integration | Activity
End Effector Design | Task
Gripper Mechanism | Subtask | 5.1.1.1.1.1.1 | R | L | P | P |  |  | 4 | 32
Sensor Integration | Subtask | 5.1.1.1.1.1.2 | R | L | P | P |  |  | 3 | 24
Control Software | Subtask | 5.1.1.1.1.1.3 | R | P | L | P |  |  | 4 | 32
Motion Planning | Task
Path Optimization | Subtask | 5.1.1.1.1.2.1 | R | P | L | P |  |  | 3 | 24
Collision Avoidance | Subtask | 5.1.1.1.1.2.2 | R | P | L | P |  |  | 4 | 32
Speed Control | Subtask | 5.1.1.1.1.2.3 | R | P | L | P |  |  | 3 | 24
Camera Setup | Activity
Lighting Design | Subtask | 5.1.1.1.2.1.1 | R | L | P | P |  |  | 3 | 24
Image Processing | Subtask | 5.1.1.1.2.1.2 | R | P | L | P |  |  | 4 | 32
Quality Checks | Subtask | 5.1.1.1.2.1.3 | R | P | P | L |  |  | 3 | 24
Project Totals |  |  | Key
Total Items: | 106 |  | L = Lead | P = Participant | R = Reviewer | I = Input | Project | Phase | Activity | Task | Subtask*
Total Phases: | 5 |  | * Subtask rows are colored to match their corresponding level in the WBS diagram
Total Activities: | 10
Total Tasks: | 23
Total Work Packages: | 67
Total Duration (Days): | 185
Total Labor (Hours): | 1480