## WBS
WBS Number | Level | Type | Name | Parent
| 0 | Project | SelfiePod
1.0 | 1 | Phase | Market Analysis | SelfiePod
1.1 | 2 | Activity | Materials Research | Market Analysis
1.1.1 | 3 | Task | Battery Research | Materials Research
1.1.1.1 | 4 | Task | Battery Types | Battery Research
1.1.1.1.1 | 5 | Task | Lithium Ion | Battery Types
1.1.1.1.1.1 | 6 | Task | Cell Chemistry | Lithium Ion
1.1.1.1.1.1.1 | 7 | Subtask | Cathode Materials | Cell Chemistry
1.1.1.1.1.1.2 | 7 | Subtask | Anode Materials | Cell Chemistry
1.1.1.1.1.1.3 | 7 | Subtask | Electrolyte Composition | Cell Chemistry
1.1.1.1.1.2 | 6 | Task | Form Factor | Lithium Ion
1.1.1.1.1.2.1 | 7 | Subtask | Cylindrical | Form Factor
1.1.1.1.1.2.2 | 7 | Subtask | Prismatic | Form Factor
1.1.1.1.1.2.3 | 7 | Subtask | Pouch | Form Factor
1.1.1.1.2.1 | 5 | Task | Safety Features | Battery Types
1.1.1.1.2.1.1 | 6 | Subtask | Thermal Management | Safety Features
1.1.1.1.2.1.2 | 6 | Subtask | Overcharge Protection | Safety Features
1.1.1.1.2.1.3 | 6 | Subtask | Short Circuit Prevention | Safety Features
1.1.1.2 | 4 | Task | Battery Capacity | Battery Research
1.1.1.2.1 | 5 | Subtask | Power Requirements | Battery Capacity
1.1.1.2.2 | 5 | Subtask | Usage Duration | Battery Capacity
1.1.1.2.3 | 5 | Subtask | Size Constraints | Battery Capacity
1.1.1.3 | 4 | Task | Battery Safety | Battery Research
1.1.1.3.1 | 5 | Subtask | Temperature Control | Battery Safety
1.1.1.3.2 | 5 | Subtask | Protection Circuits | Battery Safety
1.1.1.3.3 | 5 | Subtask | Certification Requirements | Battery Safety
1.1.1.4.1 | 4 | Subtask | Vendor Selection | Battery Research
1.1.2.1 | 3 | Task | Plastic Types | Materials Research
1.1.2.1.1 | 4 | Task | ABS Analysis | Plastic Types
1.1.2.1.1.1 | 5 | Subtask | Impact Resistance | ABS Analysis
1.1.2.1.1.2 | 5 | Subtask | Heat Resistance | ABS Analysis
1.1.2.1.1.3 | 5 | Subtask | Cost Analysis | ABS Analysis
1.1.2.1.2 | 4 | Task | Polycarbonate Study | Plastic Types
1.1.2.1.2.1 | 5 | Subtask | Durability Tests | Polycarbonate Study
1.1.2.1.2.2 | 5 | Subtask | UV Resistance | Polycarbonate Study
1.1.2.1.2.3 | 5 | Subtask | Manufacturing Process | Polycarbonate Study
1.2 | 2 | Activity | User Needs Analysis | Market Analysis
1.2.1 | 3 | Task | Target Audience Research | User Needs Analysis
1.2.1.1 | 4 | Subtask | Demographics | Target Audience Research
1.2.1.2 | 4 | Subtask | Usage Patterns | Target Audience Research
1.2.1.3 | 4 | Subtask | Purchase Behavior | Target Audience Research
1.2.2 | 3 | Task | User Pain Points | User Needs Analysis
1.2.2.1 | 4 | Subtask | Current Solutions | User Pain Points
1.2.2.2 | 4 | Subtask | Unmet Needs | User Pain Points
1.2.2.3 | 4 | Subtask | Feature Requests | User Pain Points
2.0 | 1 | Phase | Build | SelfiePod
2.1 | 2 | Activity | Component Sourcing | Build
2.1.1 | 3 | Task | Battery Procurement | Component Sourcing
2.1.1.1 | 4 | Subtask | Supplier Selection | Battery Procurement
2.1.1.2 | 4 | Subtask | Quality Verification | Battery Procurement
2.1.1.3 | 4 | Subtask | Cost Negotiation | Battery Procurement
2.1.2 | 3 | Task | Electronics Components | Component Sourcing
2.1.2.1 | 4 | Subtask | Component List | Electronics Components
2.1.2.2 | 4 | Subtask | Supplier Quotes | Electronics Components
2.1.2.3 | 4 | Subtask | Lead Time Analysis | Electronics Components
2.2 | 2 | Activity | Prototype Development | Build
2.2.1 | 3 | Task | Initial Prototype | Prototype Development
2.2.1.1 | 4 | Subtask | 3D Printing | Initial Prototype
2.2.1.2 | 4 | Subtask | Assembly | Initial Prototype
2.2.1.3 | 4 | Subtask | Testing | Initial Prototype
2.2.2 | 3 | Task | Final Prototype | Prototype Development
2.2.2.1 | 4 | Subtask | Production Methods | Final Prototype
2.2.2.2 | 4 | Subtask | Quality Control | Final Prototype
2.2.2.3 | 4 | Subtask | Documentation | Final Prototype
1.0 | 1 | Phase | Electrical Testing | SelfiePod
3.1 | 2 | Activity | Power System | Electrical Testing
3.1.1.1.1.1 | 3 | Task | Battery Performance | Power System
3.1.1.1.1.1.1 | 4 | Subtask | Charge Cycles | Battery Performance
3.1.1.1.1.1.2 | 4 | Subtask | Voltage Stability | Battery Performance
3.1.1.1.1.1.3 | 4 | Subtask | Temperature Profile | Battery Performance
3.1.1.1.1.2 | 3 | Task | Circuit Validation | Power System
3.1.1.1.1.2.1 | 4 | Subtask | Signal Integrity | Circuit Validation
3.1.1.1.1.2.2 | 4 | Subtask | EMI Testing | Circuit Validation
3.1.1.1.1.2.3 | 4 | Subtask | Power Efficiency | Circuit Validation
3.1 | 2 | Activity | MCU Validation | Electrical Testing
3.1.1.1.2.1.1 | 3 | Subtask | Clock Stability | MCU Validation
3.1.1.1.2.1.2 | 3 | Subtask | Memory Tests | MCU Validation
3.1.1.1.2.1.3 | 3 | Subtask | Peripheral Tests | MCU Validation
1.0 | 1 | Phase | Platform Strategy | SelfiePod
4.1 | 2 | Activity | Instagram Campaign | Platform Strategy
4.1.1.1.1.1 | 3 | Task | Content Creation | Instagram Campaign
4.1.1.1.1.1.1 | 4 | Subtask | Photo Shoots | Content Creation
4.1.1.1.1.1.2 | 4 | Subtask | Video Production | Content Creation
4.1.1.1.1.1.3 | 4 | Subtask | Story Templates | Content Creation
4.1.1.1.1.2 | 3 | Task | Influencer Program | Instagram Campaign
4.1.1.1.1.2.1 | 4 | Subtask | Selection Criteria | Influencer Program
4.1.1.1.1.2.2 | 4 | Subtask | Engagement Metrics | Influencer Program
4.1.1.1.1.2.3 | 4 | Subtask | ROI Analysis | Influencer Program
4.2 | 2 | Activity | TikTok Strategy | Platform Strategy
4.1.1.1.2.1 | 3 | Subtask | Trend Analysis | TikTok Strategy
4.1.1.1.2.2 | 3 | Subtask | Content Calendar | TikTok Strategy
4.1.1.1.2.3 | 3 | Subtask | Performance Metrics | TikTok Strategy
1.0 | 1 | Phase | Automation Systems | SelfiePod
5.1 | 2 | Activity | Robot Integration | Automation Systems
5.1.1.1.1.1 | 3 | Task | End Effector Design | Robot Integration
5.1.1.1.1.1.1 | 4 | Subtask | Gripper Mechanism | End Effector Design
5.1.1.1.1.1.2 | 4 | Subtask | Sensor Integration | End Effector Design
5.1.1.1.1.1.3 | 4 | Subtask | Control Software | End Effector Design
5.1.1.1.1.2 | 3 | Task | Motion Planning | Robot Integration
5.1.1.1.1.2.1 | 4 | Subtask | Path Optimization | Motion Planning
5.1.1.1.1.2.2 | 4 | Subtask | Collision Avoidance | Motion Planning
5.1.1.1.1.2.3 | 4 | Subtask | Speed Control | Motion Planning
5.1 | 2 | Activity | Camera Setup | Automation Systems
5.1.1.1.2.1.1 | 3 | Subtask | Lighting Design | Camera Setup
5.1.1.1.2.1.2 | 3 | Subtask | Image Processing | Camera Setup
5.1.1.1.2.1.3 | 3 | Subtask | Quality Checks | Camera Setup